Appendix D: 12-month plan – INFRASTRUCTURE of the ALLIANCE

Context:

Time is needed to develop the long-term formal structure and legal base for the Alliance. Therefore, in accordance with the requirement outlined by the New York meeting for some quick action, the work to formally organise the Alliance will happen in parallel to the action on impact data and policy engagement over the next 12 months as outlined above. It is important to note that the proposals below are for the next 12 months only. They are designed to both provide a clear basis for the work and decision-making that will take place over the next 12 months and to create the space to define, outline the details of, and develop the instruments that create the formal, long-term basis for the Alliance.

- Formal interim agreement  - Memorandum of Understanding (initial 12 months)

A Memorandum of Understanding (or equivalent) will be developed for the signature of the network- and partnership-based agencies and the individual organisations that will comprise the interim Alliance over the initial 12 months. That signed memorandum will include the following:

- Commitment to the mission of the Alliance.

- Commitment to work with the other organisations involved in the priority areas of policy engagement (with a focus on the HLPF), impact data, and building of the long-term structure of the Alliance.

- Agreement to co-sign the products that result from the impact data work.

- Agreement to co-sign the position paper for the HLPF and to act in alliance with the other involved organisations in relation to the overall HLPF strategy.

- On a voluntary basis, at the discretion of each organisation involved in the Alliance or supportive of the work of the Alliance, allocation of one staff day per week to the work and development of the Alliance over its initial 12 months. That staff person would need to be named and formally allocated to the Alliance in order that the team can be identified.

- Decision-making process (initial 12 months)

The following decision-making process be adopted for the initial 12 months of the Alliance:

- The meeting of the review group in Baltimore agrees on the initial networks, partnerships, associations, and individual organisations (subject to the results of the consideration of Paper 3 – Criteria above) that will be invited to form the inaugural Alliance.

- The rationale for the invitation to those organisations is clearly laid out.

- UNICEF and The Communication Initiative conduct discussions with those organisations related to their involvement.

- Each of the interested organisations is required to sign the Memorandum of Understanding (see above).

- Decisions of the Alliance comprising the invited organisations that have signed the Memorandum of Understanding require 70% agreement.

- The inaugural Alliance agrees on 2 co-Chairs of the Alliance for the initial 12 months.

- Meeting pattern (initial 12 months)

That the following meeting pattern will take place:

Full Alliance:

April 2018 – In-person around the SBCC Summit in Nusa Dua

May 2018 – Conference call

June 2018 – Conference call

July 2018 – In-person meeting perhaps in association with the High Level Political Forum

August 2018 – Conference call

September 2018 – Conference call

October 2018 – In-person meeting (hopefully in association with another event)

November 2018 – Conference call

December 2018 – Conference call

The Action Groups

The leadership and membership of the action groups focused on each of the 3 main priorities – Evidence, Policy, Infrastructue - will be agreed by Alliance. Those groups will then adopt their own working pattern.

- Interim Secretariat arrangement (initial 12 months)

Present situation

At present, the Secretariat work for the development of the Alliance is being done through a close working relationship between UNICEF (overview and strategic guidance) and The Communication Initiative (strategic discussion with UNICEF and the detailed work – for example: the field consultations; the writing of the papers and facilitation of the New York meeting; support for the Name, Criteria, and Priorities sub-groups work; and preparation, paper writing, and conducting of the Baltimore meeting).

As outlined at the New York meeting, UNICEF has contributed considerable staff time from the C4D section as well as providing funds to The Communication Initiative for the primary purpose of supporting the involvement of Warren Feek. The Communication Initiative has utilised its capacities – for example, partnership base, network, platform, e-magazines, connections to non-children and health development areas - and has also utilised some of its resources to cover additional staff time by Warren and others.

The present agreement for The Communication Initiative to undertake this work concludes in May 2018.

The Alliance will consider the secretariat arrangements for the remaining 7 months of the initial 12 month period – June to December, 2018 and make the required decisions.

- Finances (the initial 12 months)

The financing issue can distort engagement with initiatives such as this proposed Alliance. The requirement for staff time, travel costs, secretariat funding, and other basic cost can work in favour of significant engagement by the larger UN, foundation, government, and international agencies. And it can work against engagement by even the largest of the national and regional civil society organisations that work in the contexts experiencing significant development issues. We have experienced that dynamic in this process to date. The New York meeting committed to being different, given the core principles for this field of work.

Projection

Given the proposed plan of action for the initial 12 months of the Alliance, the main start-up costs will most likely involve:

- Staff time allocation by members of the Alliance related to the 3 priority areas - impact, policy influence, and developing the long-term infrastructure.

- Travel costs to meetings

- Secretariat support for the leadership/coordination to drive this process forward in a collective and organised manner.

Early in 2018 a revenue and expenditure budget will be developed for each of the 3 items above for the consideration of the January or February meeting of the Alliance based around the following principles:

- For the initial 12month period, individual organisation staff costs related to participating in the priority activities are not funded through any Alliance process.

- There is agreement in principle that the organisations involved with the larger budgets will seek to support those with much smaller budgets to participate in the in-person meetings (as UNICEF has done to date on a few occasions).

- UNICEF negotiates with other larger organisations as to which of them will take over the Secretariat funding for the final 7 months of the initial 12-month period.

- Long-term formal structure and funding base

In order to develop the long-term formal structure and negotiate the funding base for the Alliance, considerable work will need to take place. The possible tasks include:

- Identifying and negotiating a legal basis for the Alliance

- Developing the outline of a longer term (3-year) plan of action

- Agreeing and formalising participation in the Alliance

- Creating the Alliance brand identification

- Developing and negotiating the budget for the year period

- Within the boundaries and guidance outlined from the New York meeting (see below), implementing a funding plan. (Some initial thoughts follow.)

An Action Group will be formed to advance the items above. It will include members of the Alliance with appropriate support

- Long-term funding plan

Considerable care will be taken to ensure that the Alliance is not competing with other organisations for funds, as has been a key principle since the commencement of this process. This not only removes revenue streams such as membership fees from the table but also requires huge caution regarding whom to approach for funding support for the Alliance. It was for those and other reasons that the New York meeting concluded: “The majority preference was for one organisation to raise or provide new money to support a small 2-year funding arrangement for start-up purposes”

The advent of the Alliance provides an opportunity to help advance overall funding for this field of work, within which the Alliance financial requirements could be positioned. Therefore the following tasks will be undertaken by the Alliance:

- Development of a 1-page and 5-minute pitch for this field of work.

This would require considerable work to hone the language, examples, and data into the proverbial one pager with appropriate explanation. It would require considerable practice to deliver effectively. When shared, it could be of value to others across our common field of work seeking to attract the required funding.

- Take the show on the road.

Agree on a team of people (or teams – could be different teams in different contexts) to pursue major funders for meetings to hear the pitch. The chances of confirming these meetings at a high level will be greater as a collective field of work than working separately.

- Place the Alliance needs within that context.

The specific and comparatively small financial needs of the Alliance would be part of that overall pitch.